## Sheet1
|  |  |  | September | [17 empty] | October | [30 empty] | November
|  |  |  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
Task | Progress | Start | End | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
Project Initiation
Problem Identification | 100% | 2022-09-13 | 2022-09-16 | bar: September 13 S to September 16 W
Feasibility Study | 100% | 2022-09-16 | 2022-09-17 | bar: September 16 W to September 17 T
Project Planning
Plans Creation | 100% | 2022-09-16 | 2022-09-18 | bar: September 16 W to September 18 F
Analysis | 100% | 2022-09-18 | 2022-09-19 | bar: September 18 F to September 19 S
System Modelling | 100% | 2022-09-19 | 2022-09-21 | bar: September 19 S to September 21 M
Project Implementation
Coding | 87.5% | 2022-09-27 | 2022-10-28 | bar: September 27 S to October 28 W
Project Monitoring
Performance Measure | 78.5 | 2022-09-16 | 2022-10-30
Project Closure
Hand Over | 0% | 2022-10-30 | 2022-11-04 | bar: October 30 F to November 4 W